## 3-Week Forecast
Week 18 (2026-04-27 to 2026-05-03) | Available: | 168 | Planned: | 16 | Load: | 9.5%
Work Order | Eq Number | Eq Description | Type | Description | Status | Start Date | Hours
W26000009 | HTD-001 | Dump Haul Truck, 001, Epiroc, MT2010 | PM | Scheduled Maintenance | Waiting to Schedule | 2026-04-28 | 6
W26000008 | HTD-001 | Dump Haul Truck, 001, Epiroc, MT2010 | PM | Scheduled Maintenance | Waiting to Schedule | 2026-04-29 | 0
W26000007 | HTD-001 | Dump Haul Truck, 001, Epiroc, MT2010 | PM | test | Waiting to Schedule | 2026-04-27 | 0
W26000002 | HTD-001 | Dump Haul Truck, 001, Epiroc, MT2010 | CF | Replace Turbo | Waiting to Schedule | 2026-04-29 | 10
W26000005 | JDB-001 | Two Boom Jumbo, 001, Epiroc, M2C | CF | Replaced blown hose | Waiting to Schedule | 2026-04-30 | 0
Week 19 (2026-05-04 to 2026-05-10) | Available: | 180 | Planned: | 0 | Load: | 0.0%
Work Order | Eq Number | Eq Description | Type | Description | Status | Start Date | Hours
Week 20 (2026-05-11 to 2026-05-17) | Available: | 168 | Planned: | 0 | Load: | 0.0%
Work Order | Eq Number | Eq Description | Type | Description | Status | Start Date | Hours